Climate Action Plan

School Name: Newnham St Peter’s C of E Primary School 
         One year plan: Summer 2025 – Summer 2026

Your Carbon baseline: (tool down until 15/09/25)		Date: 11/09/25

| Decarbonisation and Energy Efficiency: Calculating and taking actions to reduce carbon emissions and becoming more energy efficient |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Cost benefit | Ease of implementation | Timeframe | Key stakeholders | Link to SIAMS SEF/Development Plan | Progress Track |
| Get Started |  |  |  |  |  |  |
| Sign up to Let’s Go Zero. By joining this campaign, your school confirms that it is taking action now to reduce its own carbon impact, and that it demands the UK Government help all schools reach this goal by the end of the decade. Useful links Let's Go Zero | Input: No cost Output: No savings | Easy | Start date: June 25 Review date: N/A | SLT | SIAMS IQ1 Our climate action work is an outworking of our theologically rooted Christian vision, to support a more equitable and just world and a livable future for our community. Net Zero Carbon Schools ¦ The Church of England | Completed |
| Count Your Carbon – Carbon Calculator: This free digital tool allows you to calculate the carbon footprint for your educational setting. Useful links Count Your carbon | Input: No cost Output: Potential for high savings | Moderate | Start date: June 25 Review date: September 25 | Sustainability Lead (JC) SLT/admin |  | Information gathered Summer 25. Information now needs to be submitted to the tool when it is back available 15/9/25 |
| Set up a sustainability working group and appoint a sustainability lead. | Input: No cost Output: Potential for High savings | Easy | Start date: July 25 Review date: September 25 | Sustainability Lead (JC) SBM (LT) |  | Completed |
| Energy |  |  |  |  |  |  |
| Complete the CofE Self Audit Tool to understand your buildings better and then share with your governing body Building and Energy Self Audit tool | Input: No cost Output: Potential for high savings | Easy | Start date: September 25 Review date: November 25 | JC and LT | IQ5 SIAMS Through our staff and pupil-led energy monitoring activities, our pupils and staff learn about the balance between their right to an environment conducive to learning and their responsibilities towards others in our work to mitigate climate change. Our theologically rooted Christian vision enables positive relationships that balance individual freedom and rights, with responsibility towards others through our energy reduction campaigns. |  |
| Review the practical path to Net Zero with actions and quick wins to reduce carbon for your school and add any additional quick wins to your plan | Input: No cost for tool. Actions might involve some cost Output: Potential for high savings | Easy | Start date: September 25 Review date: November 25 | JC |  |  |
| Set your BMS/BEMS appropriately in the evenings, weekends and school holidays, when the building may be out of use | Input: No cost Output: Moderate | Easy | Start date: Autumn 25 Review date: Spring 26 | JC and LT |  |  |
| Instruct all staff to follow heating efficiency practices eg turn heating down vs opening windows | Input: No cost Output: Moderate | Easy | Start date: Autumn 25 Review date: Spring 26 | JC |  |  |
| Take part in a switch off campaign e.g. Switch off Fortnight. Aim for 10% reduction of energy use (the typical amount saved by participating schools). | Input: Free Output: moderate | Moderate | Start date: Spring 26 Review date: Summer 26 | JC and LT |  |  |
| Food |  |  |  |  |  |  |
| Weigh food waste from kitchen and plates and share results Energy Sparks have a free resource here on how to run a lunchtime audit, as well resources for running a food waste assembly.​ | Input: Low Output: moderate | Moderate | Start: Spring 26 Review: Summer 26 | JC and LT | IQ4 SIAMS and IQ5 SIAMS Our school policies on providing a healthy low carbon menu, creates a culture in which people’s wellbeing is enhanced. Our staff and pupils understand that through their daily menu choices, they can be a powerful advocate for not just their own health, but the future of a healthy planet. |  |
| Sign up for Taste Ed workshops Taste Ed do free workshops for primary schools, encouraging children to try different fruits and vegetables.​ | Cost: None Savings: None | Moderate | Start: Summer 26 Review: Summer 26 | Class Teachers |  |  |
| Waste |  |  |  |  |  |  |
| Install a compost bin for garden waste and fruit Glocs CC have free compost bins available for schools and can also arrange for their Waste Minimisation Officer or one of their Master Composters to visit the school to advise on how to get started and maintain your composting system. ​ | Input: Free Output: none | Easy | Start: Autumn 25 Review: Spring 25 | JC and LT | SIAMS IQ5 Through our staff and pupil-led action on waste reduction our staff and pupils take responsibility as stewards of our world. Our Sustainability work is one of a range of strategies to ensure that this stewardship fits within our theologically rooted Christian vision and is a living reality that enables pupils and adults to flourish. |  |
| Label bins clearly Food bins in each class room and outside. Eco team to ensure all use the correct bins. | Input: minimal cost Output: none | Easy | Start date: Autumn 25 Review date: Spring 25 | JC and LT |  |  |
| Procurement |  |  |  |  |  |  |
| Factor in energy efficiency when buying new equipment such as ovens, fridges, kettles (using efficiency ratings to guide purchases) | Input: No cost Output: No savings | Easy | Start: Autumn ‘25 Review: Spring 25 | JC and LT | IQ5d: Through our school’s strategic policies for ethical purchasing, we identify systems to reduce unnecessary consumption and therefore reduce our impact on the world’s resources. In making these choices, we create an active culture of justice and responsibility and through this, the trust makes a positive impact on the culture of the school. |  |
| Reuse school uniform through a uniform exchange and second hand uniform sales Let’s Go Guide | Input: No cost Output: No savings | Easy | Start: Autumn ‘25 Review: Spring 25 | JC and LT |  |  |
| Transport |  |  |  |  |  |  |
| Conduct a staff and student travel survey | Input: No cost Output: No savings | Easy/ Moderate | Start: Spring 26 Review: Summer 26 | JC and Class teachers | SIAMS IQ4 and SIAMS IQ5 Through our staff and pupils’ engagement in active travel weeks, with students leading the way to petition for safer school walking routes, better public transport and reducing car use, our school culture encourages justice and courageous advocacy, enabling pupils to make ethical choices and to be agents of change. |  |
| Hold a walk to school week | Input: No cost Output: No savings | Easy/ Moderate | Start: Spring 26 Review: Summer 26 | JC and Class teachers |  |  |
| Provide cycle proficiency lessons in school e.g. Bikeability | Input: Small cost Output: No savings | Easy | Start: Spring 26 Review: Summer 26 | JC |  |  |

| Climate Adaptation and Resilience: Taking actions to reduce the risk of flooding and overheating and to future-proof scarce resources for potential shortages |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Cost | Ease of implementation | Timeframe | Key stakeholders | Link to School improvement plan | Progress Track |
| Water |  |  |  |  |  |  |
| Raise awareness around consumption and efficiency through workshops and displays | Input: Free Output: Low | Easy | Start date: Autumn 25 Review date: Spring 25 | LB Eco team SLT | Q4a: Through our pupil-led work on conserving water both in our school and grounds, supports our pupils to understand the precious and precarious balance of life and our responsibilities to it. We link our water use with the impact of climate change on the world’s most vulnerable communities. Through this, our theologically rooted Christian vision enables all to live well together in an inclusive, dignifying, and equitable culture. |  |
| Adaptation and Resilience |  |  |  |  |  |  |
| Write a heatwave policy that addresses areas such as school dress code, passive ventilation measures and PE lessons | Input: Free Output: Low | Moderate | Start date: Spring 25 Review date: Summer 25 | LB SLT LAC | IQ1 Our theologically rooted Christian vision is a living reality that enables pupils and students, communities and nature to flourish in a changing climate. By planning to adapt and being more resilient to the impacts of climate change we ensure the health, safety and wellbeing of our school and wider community. |  |

| Biodiversity and Green Infrastructure: Creating habitats and adopting practices that will enhance species diversity on the school estate and beyond |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Cost | Ease of implementation | Timeframe | Key stakeholders | Link to School improvement plan | Progress Track |
| Nature |  |  |  |  |  |  |
| Continue with a gardening/ nature club | Input: No cost Output: No savings | Easy | Start date: Autumn 25 Review date: Spring 25 | LB SLT SM | IQ3c: By taking opportunities to worship outdoors, within nature and surrounded by the wonder of the world, we ensure that the worship life of the school inclusive, invitational, and inspirational. IQ4d: As a result of the theologically rooted Christian vision, our provision of opportunities to work in nature for our pupils with SEND, (or those who are vulnerable and/or disadvantaged) is one of our most effective strategies to help at difficult times. Pupils learn to self-regulate and maintain healthy emotions within these times and spaces in our garden. IQ4 SIAMS Mental health and wellbeing |  |
| Carry out a biodiversity survey of the school site Utilise apps such as Merlin Bird ID and Seek. Consider how you might involve parents and/or the wider community perhaps via a ‘bio-blitz’ day?​ | Input: No cost Output: No savings | Easy | Start date: Spring 25 Review date: Summer 25 | LB SLT SM |  |  |

| Climate Education, Green Skills and Green careers: Ensuring the education you provide gives knowledge-rich and comprehensive teaching about climate change, and that your teaching staff feel supported to offer this |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Cost | Ease of implementation | Timeframe | Key stakeholders | Link to SIAMS SEF | Progress Track |
| Curriculum |  |  |  |  |  |  |
| Complete a curriculum audit and incorporate sustainability Teach the Future have amazing resources on how to link the curriculum to sustainability. MoEE also has very helpful resources on this, and The Harmony Project has some lovely nature based resources. | Input: No cost Output: No savings | Moderate | Start: Autumn 25 Review: Spring 25 | SLT | SIAMS IQ2 Our school’s theologically rooted Christian vision shapes our curriculum offer as well as our enrichment offer. Through these additional opportunities, our pupils and staff strengthen their understanding of climate change and how we can mitigate this and protect God’s world SIAMS IQ3 Collective Worship and Spirituality IQ6 and IQ7 RE |  |
| Survey staff on how they feel about teaching sustainability issues | Input: No cost Output: No savings | Moderate | Start: Autumn 25 Review: Spring 25 | SLT |  |  |
| Culture |  |  |  |  |  |  |
| Provide CPD opportunities for staff on sustainability Include sustainability networks and events in your staff CPD offer and encourage and support staff to attend. You can include Let's Go Zero's webinar schedule in your CPD offer plus events from UKSSN, National Education Nature Park and other offers local to your school. | Input: No cost Output: No savings | Easy | Start: Spring 25 Review: Summer 25 | SLT | SIAMS IQ1 Our climate action work is an outworking of our theologically rooted Christian vision, to support a more equitable and just world and to enable all our adults and young people to flourish, both now and for future generations |  |

Let’s Go Zero contact details:

Email: hello@letsgozero.org

Website: letsgozero.org

letsgozero.org

Ashden is registered in England and Wales as a company limited by guarantee.

Registered number: 05062574/ Charity number: 1104153

The Peak, 3rd Floor 5 Wilton Road, London, SW1V 1AP